## Worksheet
Task | Owner | Start Date | End Date | Status | Notes
Project Kickoff Meeting | Alex Johnson | 2024-03-01 | 2024-03-01 | Completed | All stakeholders aligned on goals and scope.
Requirements Gathering | Maria Lopez | 2024-03-02 | 2024-03-15 | In Progress | Collecting user needs via interviews and surveys.
Design Mockups | Samir Patel | 2024-03-16 | 2024-03-25 | Pending Review | Final designs to be reviewed by PM and UX team.
Development Phase | Team A (Freelancers) | 2024-03-26 | 2024-04-15 | Not Started | Frontend and backend development to begin.
QA Testing | Jordan Kim | 2024-04-16 | 2024-04-25 | Not Started | Bug tracking and performance testing.
Client Review & Feedback | Alex Johnson | 2024-04-26 | 2024-05-03 | Not Started | Final approval and feedback collection.
Go-Live Deployment | Team B (Freelancers) | 2024-05-04 | 2024-05-04 | Planned | Deployment to production environment.