## Worksheet
Task | Owner | Start Date | End Date | Status | Notes
Project Kickoff Meeting | Alex Johnson | 2024-03-15 | 2024-03-15 | Completed | All team members present and objectives agreed.
Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | In Progress | Initial interviews with stakeholders completed.
Design Phase | Mike Chen | 2024-03-26 | 2024-04-10 | Planned | Wireframes and UI mockups to be shared by April 5.
Development Phase | Team A & B | 2024-04-11 | 2024-05-30 | Not Started | Codebase setup in progress; sprint planning scheduled.
Testing & QA | Linda Patel | 2024-06-01 | 2024-06-15 | Not Started | Beta version to be deployed for internal testing.
Final Review & Launch | All Team | 2024-06-16 | 2024-06-18 | Planned | Final presentation to stakeholders and public launch.