## Worksheet
Task | Responsible Team | Start Date | End Date | Status | Priority | Milestones
Project Initiation & Planning | Strategy & Planning Team | 2024-03-01 | 2024-03-15 | In Progress | High | Kickoff Meeting, Scope Definition
Market Research & Analysis | Research & Insights Team | 2024-03-16 | 2024-04-05 | On Track | High | Data Collection, Competitor Review
Product Design & Prototyping | Design & UX Team | 2024-04-06 | 2024-05-10 | Planned | Medium | Wireframes Approved, Prototype Demo
Development & Build Phase | Engineering Team | 2024-05-11 | 2024-07-30 | Scheduled | High | Alpha Release, Beta Testing Start
User Testing & Feedback Loop | Product & QA Team | 2024-08-01 | 2024-08-31 | Pending | High | Final Feedback Collection, Iteration Planning
Launch & Post-Launch Support | Operations & Marketing Team | 2024-09-01 | 2024-09-30 | Not Started | Critical | Go-Live, Customer Onboarding, Support Setup