## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Milestones
Project Kickoff Meeting | Sarah Johnson | 2024-03-01 | 2024-03-01 | Completed | 100% | None | Kickoff Approved
Requirement Gathering | Michael Chen | 2024-03-02 | 2024-03-15 | In Progress | 65% | Kickoff Meeting
Design Phase | Emma Rodriguez | 2024-03-16 | 2024-04-10 | Planned | 0% | Requirement Finalized | Design Review
Development Phase | Team A (Dev) | 2024-04-11 | 2024-06-15 | Not Started | 0% | Design Approved
Testing & QA | Lena Kim | 2024-06-16 | 2024-07-10 | Planned | 0% | Development Complete | QA Sign-off
Deployment & Go-Live | David Patel | 2024-07-11 | 2024-07-15 | Not Started | 0% | QA Passed | Go-Live Event