## Worksheet
Month | Project Phase | Key Activities | Team Responsibilities | Milestones | Deadlines | Status (Monthly)
January | Project Initiation & Planning | Define objectives, scope, and budget; conduct stakeholder workshops | Project Manager, Stakeholder Leads, Finance Team | Finalized project charter; approved budget | January 31 | On Track
February | Requirements Gathering & Analysis | Collect user needs; document functional and non-functional requirements | Product Owner, UX Team, Business Analysts | Completed requirement specification document | February 28 | On Track
March | Design & Prototyping | Create wireframes and UI mockups; conduct user testing sessions | Design Team, UX Researchers, Development Lead | Approved UI design package; usability test results reviewed | March 31 | On Track
April | Development & Integration | Build core features; integrate with backend systems and APIs | Development Team, QA Engineers, DevOps | Core module completed; integration testing started | April 30 | On Track
May | Testing & Quality Assurance | Conduct unit, integration, and user acceptance testing | QA Team, Test Leads, Product Owner | All critical bugs resolved; UAT sign-off achieved | May 31 | On Track
June | Deployment & Launch Prep | Prepare staging environment; finalize user training materials | DevOps, Training Team, Marketing | Production environment ready; launch plan approved | June 30 | On Track
July | Go-Live & Post-Launch Support | Deploy to production; monitor system performance and user feedback | Operations, Customer Support, IT Team | Successful go-live; initial performance metrics reported | July 31 | On Track