## Worksheet
Project Phase | Team Member | Start Date | End Date | Status | Key Deliverables | Responsible Owner
Discovery & Planning | Product Manager, UX Designer | 2024-03-01 | 2024-03-15 | Completed | Market research, user personas, scope document | Anna Reyes
Design & Prototyping | UI/UX Designer, Interaction Designer | 2024-03-16 | 2024-04-10 | In Progress | Figma prototypes, wireframes, design system | Liam Chen
Development Phase | Frontend Dev, Backend Dev, QA Engineer | 2024-04-11 | 2024-06-30 | Planned | Core features implementation, API integrations | Sophia Kim
Testing & Quality Assurance | QA Engineer, Product Owner | 2024-07-01 | 2024-07-31 | Not Started | User acceptance testing, bug fixes, performance reviews | Marcus Bell
Launch & Post-Launch Support | Project Manager, DevOps, Customer Support | 2024-08-01 | 2024-08-31 | Scheduled | Landing page deployment, user training materials, feedback loop setup | David Torres
Team Collaboration – Project Timeline (Multi-Page Template)