## Worksheet
Task | Responsible Team | Start Date | End Date | Status | Progress %
Project Kickoff Meeting | Project Management Team | 2024-03-01 | 2024-03-05 | Completed | 100%
Requirement Gathering Phase | Product & UX Team | 2024-03-06 | 2024-03-15 | In Progress | 65%
Design & Wireframing | Design Team | 2024-03-16 | 2024-03-30 | Not Started | 0%
Development Phase (Phase 1) | Engineering Team | 2024-04-01 | 2024-04-30 | Not Started | 0%
Testing & Quality Assurance | QA Team | 2024-05-01 | 2024-05-31 | Not Started | 0%
Project Review & Go-Live | All Teams | 2024-06-01 | 2024-06-30 | Not Started | 0%