## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | 2024-04-01 | Completed | None
Requirements Gathering | Sara Lee | 2024-04-02 | 2024-04-15 | In Progress | Kickoff Meeting
Design Phase | Mike Chen | 2024-04-16 | 2024-05-05 | Planned | Requirements Gathering
Development Start | Team A (Dev) | 2024-05-06 | 2024-06-15 | Not Started | Design Phase
Testing & QA | Lena Patel | 2024-06-16 | 2024-07-10 | Planned | Development Start
Project Review & Delivery | Alex Johnson | 2024-07-11 | 2024-07-15 | Not Started | Testing & QA