## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Maria Lopez | 2024-03-01 | 2024-03-01 | Completed
Requirements Gathering | David Chen | 2024-03-04 | 2024-03-15 | In Progress | Kickoff Meeting
Design Phase Review | Sophia Kim | 2024-03-18 | 2024-03-25 | Planned | Requirements Gathering
Development Sprint 1 | Team A | 2024-03-26 | 2024-04-05 | Not Started | Design Phase Review
Testing & QA Cycle | James Reed | 2024-04-08 | 2024-04-18 | Scheduled | Development Sprint 1
User Training Session | Linda Wong | 2024-04-20 | 2024-04-21 | Not Started | Testing & QA Cycle
Go-Live Deployment | Project Manager | 2024-04-25 | 2024-04-25 | Planned | User Training Session