## Worksheet
Task | Responsible Team | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Project Leadership Team | 2024-03-15 | 2024-03-15 | Completed | None
Requirements Gathering | Product & UX Team | 2024-03-16 | 2024-03-31 | In Progress | Kickoff Meeting
Design Phase Completion | UI/UX Design Team | 2024-04-01 | 2024-04-15 | Planned | Requirements Gathering
Development Sprint 1 | Engineering Team | 2024-04-16 | 2024-05-03 | Scheduled | Design Phase Completion
Testing & QA Review | QA Team | 2024-05-04 | 2024-05-17 | Not Started | Development Sprint 1
Stakeholder Feedback & Adjustments | Product & Leadership Team | 2024-05-18 | 2024-05-24 | Planned | Testing & QA Review
Final Deployment & Launch | All Teams (Deployment Team) | 2024-05-25 | 2024-05-31 | Scheduled | Stakeholder Feedback & Adjustments