## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Sarah Johnson | 2024-03-01 | 2024-03-01 | Completed | None
Scope Definition & Stakeholder Alignment | Michael Chen | 2024-03-04 | 2024-03-10 | Kickoff Meeting | Project Kickoff Meeting
Requirements Gathering Workshop | Lisa Rodriguez | 2024-03-11 | 2024-03-15 | Scope Definition | Scope Definition & Stakeholder Alignment
Design Phase Planning | David Kim | 2024-03-18 | 2024-03-25 | Requirements Gathering | Requirements Gathering Workshop
Prototype Development | Emma Watson | 2024-03-26 | 2024-04-05 | Design Phase Planning | Design Phase Planning
User Testing & Feedback Collection | James Wilson | 2024-04-06 | 2024-04-15 | Prototype Development | Prototype Development
Final Review & Approval | Team Leadership | 2024-04-16 | 2024-04-18 | User Testing | User Testing & Feedback Collection
Go-Live & Deployment | Operations Team | 2024-04-19 | 2024-04-20 | Final Review | Final Review & Approval