## Worksheet
Quarter | Team Objective | Key Activities | Milestones | Responsible Team Members | Deadline (MM/DD)
Q1 – Jan to Mar | Launch Project Phase One | - Finalize project scope - Conduct stakeholder interviews - Develop initial roadmap | - Scope approval (March 15) - Roadmap finalized (March 30) | Project Manager, Product Lead | 03/30
Q2 – Apr to Jun | Develop Core Features | - Design UI/UX prototypes - Build MVP functionality - Conduct internal testing | - Prototype review (May 10) - MVP ready (June 15) | Design Team, Engineering Lead | 06/15
Q3 – Jul to Sep | User Testing & Feedback Loop | - Beta launch with 50 users - Collect feedback via surveys - Refine features based on data | - Beta phase complete (August 20) - Final feature update (September 10) | QA Team, UX Analyst | 09/10
Q4 – Oct to Dec | Full Launch & Performance Review | - Public launch - Monitor KPIs and user engagement - Generate post-launch report | - Full launch (October 30) - Final review report submitted (December 15) | Marketing, Operations Team | 12/15