## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%)
Project Kickoff Meeting | Alex Morgan | 2024-03-15 | 2024-03-15 | Completed |  | 100%
Requirements Gathering | Jamie Lee | 2024-03-16 | 2024-03-31 | In Progress | Meeting with stakeholders | 75%
Design Phase (UI/UX) | Samira Patel | 2024-04-01 | 2024-04-15 | Planned | Requirements finalized | 0%
Development Sprint 1 | Ryan Chen | 2024-04-16 | 2024-05-03 | Scheduled | Design approved | 0%
Testing & Quality Assurance | Lena Torres | 2024-05-04 | 2024-05-18 | Not Started | Development complete | 0%
Final Review & Deployment | Team Lead | 2024-05-19 | 2024-05-25 | Planned | Testing completed | 0%