## Worksheet
Task | Responsible | Start Date | End Date | Status
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-01 | Completed
Requirements Gathering | Product Owner | 2024-03-02 | 2024-03-15 | In Progress
Design Phase | UX Designer | 2024-03-16 | 2024-03-31 | Planned
Development Start | Development Team | 2024-04-01 | 2024-05-15 | Not Started
Testing & QA | QA Team | 2024-05-16 | 2024-06-05 | Planned
Final Review & Deployment | Project Manager | 2024-06-06 | 2024-06-10 | Not Started