## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Product Vision Finalization | Alex Rivera | 2024-03-15 | 2024-03-25 | In Progress | -
Market Research & Competitor Analysis | Jordan Lee | 2024-03-20 | 2024-04-05 | Pending | Product Vision Finalization
Wireframing & UI Mockups | Mia Chen | 2024-04-10 | 2024-04-30 | Not Started | Market Research & Competitor Analysis
Development Sprint (Phase 1) | Team Core | 2024-05-01 | 2024-05-31 | Planned | Wireframing & UI Mockups
User Testing & Feedback Loop | Sam Patel | 2024-06-15 | 2024-06-30 | Not Started | Development Sprint (Phase 1)
Beta Launch & Iteration | All Team Members | 2024-07-10 | 2024-07-31 | Pending | User Testing & Feedback Loop