## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress %
Project Kickoff Meeting | Sarah Johnson | 2024-03-15 | 2024-03-15 | Completed | None | 100%
Requirements Gathering | Mike Chen | 2024-03-16 | 2024-03-31 | In Progress | Kickoff Meeting | 65%
Design Phase | Lisa Patel | 2024-04-01 | 2024-04-15 | Not Started | Requirements Gathering | 0%
Development Sprint 1 | Team A | 2024-04-16 | 2024-05-10 | Planned | Design Phase | 0%
Testing & QA Review | David Kim | 2024-05-11 | 2024-05-30 | Not Started | Development Sprint 1 | 0%
Project Delivery & Handover | Sarah Johnson | 2024-06-01 | 2024-06-15 | Planned | Testing & QA Review | 0%