## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Team Notes
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | 2024-04-01 | Completed | None | All team members confirmed. Goals and roles assigned.
Requirements Gathering | Sarah Chen | 2024-04-02 | 2024-04-15 | In Progress | Kickoff Meeting | Stakeholders engaged. Draft requirements reviewed in team sync.
Design Phase (Wireframes) | David Kim | 2024-04-16 | 2024-04-25 | Planned | Requirements Finalized | Team will present wireframes in next sprint planning.
Development Sprint 1 | Team A | 2024-05-01 | 2024-05-15 | Not Started | Design Phase Complete | Frontend and backend modules will be built in parallel.
QA Testing & Bug Fixes | Emily Rao | 2024-05-16 | 2024-05-31 | Planned | Development Sprint 1 Complete | All critical bugs to be resolved before user acceptance.
User Acceptance & Feedback | Team B | 2024-06-01 | 2024-06-15 | Not Started | QA Testing Complete | Final feedback collected from pilot users. Updates will be documented.