## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | Completed | 100% | None
Requirements Gathering | Mark Johnson | 2024-03-16 | 2024-03-31 | In Progress | 75% | Kickoff Meeting
Design Phase | Lisa Chen | 2024-04-01 | 2024-04-15 | Pending | 0% | Requirements Finalized
Development Start | Team A | 2024-04-16 | 2024-05-31 | Planned | 0% | Design Phase Complete
Testing & QA | David Lee | 2024-06-01 | 2024-06-30 | Not Started | 0% | Development Complete
Project Review & Delivery | Project Manager | 2024-07-01 | 2024-07-15 | Scheduled | 0% | Testing Complete