## Worksheet
Task ID | Task Name | Owner | Team Member(s) | Status | Priority | Due Date | Progress (%) | Estimated Hours | Actual Hours | Comments
T-001 | Define Project Scope | Alex Rivera | Sara Lee, Jordan Kim | In Progress | High | 2024-04-15 | 65% | 8 | 6 | Initial scope draft reviewed by stakeholders.
T-002 | Design User Interface | Mia Thompson | Liam Chen, Chloe Wu | Pending | Medium | 2024-04-25 | 0% | 16 | 0 | Waiting for approval of design guidelines.
T-003 | Develop Backend API | Ryan Park | Nina Patel, David Zhao | In Progress | High | 2024-05-05 | 40% | 24 | 12 | Integration with authentication module completed.
T-004 | Conduct User Testing | Elena Gomez | Samira Ali, Tom Reed | Not Started | High | 2024-05-15 | 0% | 8 | 0 | Need to finalize UI mockups before testing.
T-005 | Project Kickoff Meeting | Sarah Johnson | All Team Members | Completed | Low | 2024-04-05 | 100% | 4 | 4 | All roles and responsibilities confirmed.