## Worksheet
Task | Assigned To | Due Date | Status | Progress (%) | Notes
Project Kickoff Meeting | John Doe | 2023-10-01 | Completed | 100% | All team members signed off.
Requirements Gathering | Jane Smith | 2023-10-15 | In Progress | 60% | Final review scheduled for 10/14.
Design Phase | Alex Johnson | 2023-11-05 | Not Started | 0% | Initial wireframes to be submitted by 10/30.
Development Start | Team A | 2023-11-15 | Not Started | 0% | Setup environments and code repositories.
Testing & Quality Assurance | Lisa Chen | 2023-12-01 | Not Started | 0% | All features to be tested by end of Nov.