## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Define project scope and objectives | Anna Lopez | 2024-03-15 | In Progress | High | 60%
Finalize team roles and responsibilities | James Kim | 2024-03-20 | Pending | Middle | 0%
Conduct stakeholder workshop | Sophia Chen | 2024-03-25 | Not Started | High | 0%
Create project timeline and milestones | Marcus Reed | 2024-03-30 | In Progress | High | 45%
Review and approve project budget | Lena Torres | 2024-04-05 | Pending | Middle | 0%