## Worksheet
Task | Team Member | Assigned Date | Due Date | Status | Progress (%) | Notes
Project Planning Meeting | Alex Johnson | 2023-10-01 | 2023-10-05 | Completed | 100% | All objectives agreed upon.
Design Phase Finalization | Samira Patel | 2023-10-06 | 2023-10-15 | In Progress | 75% | Design mockups reviewed by UX team.
Development Sprint 1 | Jordan Lee | 2023-10-16 | 2023-10-25 | Not Started | 0% | Waiting for design approvals.
User Testing Session | Morgan Clark | 2023-10-26 | 2023-11-05 | Planned | 0% | To be scheduled with stakeholders.
Final Review & Go-Live | Team Leadership | 2023-11-06 | 2023-11-15 | Not Started | 0% | All feedback to be integrated.