## Worksheet
Task | Assigned To | Due Date | Status | Progress (%) | Priority | Comments
Project Kickoff Meeting | Alex Johnson | 2024-04-10 | Completed | 100% | High | All stakeholders aligned on goals and timelines.
Market Research Analysis | Samantha Lee | 2024-04-25 | In Progress | 65% | Medium | Data collection completed; awaiting feedback from sales team.
UI/UX Wireframes Finalization | Jordan Patel | 2024-05-05 | Pending | 30% | High | Initial drafts shared; waiting for design review.
Development Phase Planning | Morgan Taylor | 2024-05-10 | Not Started | 0% | High | Team will meet to define sprint goals and tech stack.
Post-Launch Review Meeting | All Team Members | 2024-06-15 | Planned | 0% | Medium | To evaluate performance metrics and gather user feedback.