## Worksheet
Task | Assigned To | Due Date | Status | Progress (%) | Notes
Project Kickoff Meeting | Alex Johnson | 2023-10-05 | Completed | 100% | All team members present and goals agreed.
Design Phase Planning | Sam Rivera | 2023-10-15 | In Progress | 60% | Wireframes approved by UX team.
Develop MVP Features | Jordan Lee | 2023-11-05 | Not Started | 0% | Feature list finalized. Waiting for design assets.
Team Retrospective (Monthly) | All Team | 2023-10-25 | Completed | 100% | Key improvements noted and action items documented.
Client Feedback Review | Mia Chen | 2023-11-10 | Pending | 30% | Waiting for client response via email.