## Worksheet
Project ID | Project Name | Team Members | Start Date | End Date | Status | Priority | Progress (%) | Next Action | Responsible Owner
PRJ-2024-001 | Customer Onboarding Platform Launch | Alex Morgan, Samira Patel, Jordan Lee | 2024-03-01 | 2024-07-30 | Active | High | 75% | Finalize UI Design Review | Samira Patel
PRJ-2024-002 | Cross-Departmental Analytics Dashboard | Morgan King, Elena Ruiz, David Chen | 2024-04-05 | 2024-09-15 | Planning | Medium | 30% | Define KPIs and Data Sources | David Chen
PRJ-2024-003 | Global Marketing Campaign Rollout | Taylor Reed, Jordan Lee, Naomi Kim | 2024-05-01 | 2024-10-31 | In Progress | High | 55% | Complete regional strategy approval | Taylor Reed
PRJ-2024-004 | Internal Process Automation Initiative | Marcus Wright, Sophia Lee, Kevin Moore | 2024-03-15 | 2024-12-31 | Pending Approval | Critical | 20% | Submit budget proposal to CFO | Marcus Wright