## Worksheet
Task | Owner | Status | Deadline | Progress (%) | Dependencies | Priority
Project Kickoff Meeting | Jane Doe | Completed | 2023-10-05 | 100% | None | High
Market Research Analysis | Mike Smith | In Progress | 2023-10-15 | 60% | Project Kickoff Meeting | Medium
UI/UX Design Finalization | Lisa Chen | Not Started | 2023-11-05 | 0% | Market Research Analysis | High
Development Sprint 1 | Team A | Scheduled | 2023-11-15 | 0% | UI/UX Design Finalization | High
QA Testing Phase | Sarah Lee | Not Started | 2023-12-05 | 0% | Development Sprint 1 | Medium
Project Review & Launch | John Brown | Planned | 2023-12-15 | 0% | QA Testing Phase | High