## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Team Notes
Define Project Scope | Alice Johnson | 2024-03-15 | In Progress | High | 65% | Final stakeholders to be confirmed by March 10.
Develop Project Timeline | Bob Smith | 2024-03-20 | Not Started | Medium | 0% | Initial draft to be shared with team on March 12.
Assign Team Roles | Carol Lee | 2024-03-18 | In Progress | High | 40% | Role clarity needs feedback from department heads.
Conduct Kickoff Meeting | David Brown | 2024-03-25 | Scheduled | Medium | 0% | Meeting agenda to be finalized by March 20.
Review Budget Allocation | Elena Garcia | 2024-03-30 | Not Started | High | 0% | Needs alignment with finance team.