## Worksheet
Task | Assignee | Due Date | Status | Progress (%) | Comments
Project Kickoff Meeting | Alice Johnson | 2024-04-01 | Completed | 100% | All team members confirmed attendance.
Requirements Gathering | Bob Smith | 2024-04-15 | In Progress | 60% | Finalizing user stories and acceptance criteria.
Design Phase | Carol Davis | 2024-05-01 | Not Started | 0% | Wireframes and UI mockups to be created.
Development Phase | David Lee | 2024-06-15 | Planned | 0% | Team to be assigned in next sprint planning.
Testing & QA | Eva Wong | 2024-07-10 | Not Started | 0% | Manual and automated tests scheduled after development.
Deployment | Frank Miller | 2024-07-30 | Not Started | 0% | Scheduled post-test approval.