## Worksheet
Task | Assigned To | Due Date | Status | Priority | Progress (%) | Notes
Project Kickoff Meeting | Team Lead | 2024-04-01 | Completed | High | 100% | Initial alignment with stakeholders.
Requirements Gathering | Product Manager | 2024-04-15 | In Progress | High | 65% | Feedback from UX team pending.
Design Approval | UX Designer | 2024-04-20 | Pending | Medium | 30% | Waiting for stakeholder review.
Development Phase Start | Dev Team | 2024-05-01 | Not Started | High | 0% | Set up development environment.
Testing & QA | QA Lead | 2024-05-15 | Not Started | Medium | 0% | Will begin after development completes.
Final Review & Launch | Project Manager | 2024-05-30 | Not Started | High | 0% | Final sign-off and deployment.