## Worksheet
Task | Owner | Status | Priority | Due Date | Progress (%) | Notes
Project Kickoff Meeting | Jane Doe | Completed | Low | 2023-10-01 | 100% | All stakeholders aligned on goals.
Requirements Gathering | Mark Smith | In Progress | High | 2023-10-15 | 60% | Finalizing user stories and acceptance criteria.
Design Approval | Lisa Chen | Pending | Medium | 2023-10-25 | 0% | Waiting for client feedback.
Development Start | Team A | Not Started | High | 2023-11-05 | 0% | Backend setup and API integration.
QA Testing Phase | Robert Kim | Not Started | Medium | 2023-11-20 | 0% | Will begin after development completion.