## Worksheet
Week | Team Member | Task | Status | Assigned Date | Due Date | Progress (%) | Notes
Week 1 | Alex Johnson | Project Kickoff Meeting | Completed | 2023-10-01 | 2023-10-05 | 100%
Week 1 | Sam Rivera | Requirements Gathering | In Progress | 2023-10-02 | 2023-10-14 | 65% | Need input from UX team.
Week 2 | Jamie Lee | Design Mockups | Pending | 2023-10-06 | 2023-10-21 | 0% | Waiting on stakeholder feedback.
Week 2 | Taylor White | Development Setup | Completed | 2023-10-08 | 2023-10-15 | 100%
Week 3 | Jordan Park | API Integration Testing | Not Started | 2023-10-16 | 2023-10-30 | 0% | Schedule to begin after QA review.