## Worksheet
Task | Owner | Due Date | Priority | Status | Notes / Details
Schedule weekly team meeting | Sarah Johnson | 2024-04-15 | Medium | In Progress | Agenda to be shared one day prior. Include action items from last meeting.
Create shared project folder on cloud | Mark Thompson | 2024-04-10 | High | Completed | Folder now accessible to all team members with links shared via email.
Define collaboration tools (e.g., Slack, Trello) | Lisa Chen | 2024-04-20 | Medium | Not Started | Draft proposal under review; will present to leadership on 15 April.
Set up team communication protocol | David Reed | 2024-04-18 | High | In Progress | Draft approved; waiting for final sign-off from HR.
Conduct team onboarding session | Rachel Kim | 2024-04-25 | Medium | Planned | Includes new hires and remote team members. Materials to be prepared by 18 April.