## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Progress (%) | Team Owner | Comments
T001 | Design User Interface Mockups | Sarah Chen | High | 2023-10-15 | In Progress | 65% | Alex Rivera | Feedback from stakeholders included in v2.0.
T002 | Conduct Weekly Team Sync Meeting | Jordan Lee | <Medium | 2023-10-18 | Completed | 100% | Alex Rivera | Meeting notes shared via shared drive.
T003 | Develop Backend API Integration | Morgan Patel | High | 2023-11-05 | Not Started | 0% | Jordan Lee | Requires security review before development.
T004 | Organize Product Roadmap Workshop | Taylor Kim | Medium | 2023-10-25 | Scheduled | 0% | Alex Rivera | Participants confirmed. Agenda pending.
T005 | Review QA Test Cases | Casey Wu | Low | 2023-11-01 | In Progress | 40% | Morgan Patel | Testing environment ready. Initial feedback collected.