## Worksheet
Task ID | Task Title | Assigned To | Priority | Due Date | Status | Progress (%) | Team Member Comments
T001 | Design UI Mockups | Anna Smith | High | 2024-04-15 | In Progress | 65% | Feedback requested on layout consistency.
T002 | Develop Backend API | James Lee | High | <2024-04-20 | Completed | 100%
T003 | User Onboarding Flow | Sophia Chen | Medium | 2024-05-01 | Planned | 0% | Need input from UX team.
T004 | Performance Optimization | Michael Park | High | 2024-04-30 | In Progress | 40% | Testing in staging environment.
T005 | Team Retrospective Meeting | All Team Members | Low | 2024-04-28 | Completed | 100% | Key insights shared on communication gaps.