## Worksheet
Task ID | Task Title | Assigned To | Priority | Due Date | Status | Progress (%) | Team Notes
T-001 | Finalize Q3 Marketing Strategy | Sarah Johnson | High | 2023-09-30 | In Progress | 65% | Align messaging with product updates and customer feedback.
T-002 | Conduct Customer Satisfaction Survey | David Lee | Medium | 2023-09-25 | Pending | 0% | Needs approval from legal to include specific questions.
T-003 | Develop UX Wireframes for New Portal | Lisa Chen | High | 2023-09-28 | Not Started | 0% | Include accessibility compliance checks.
T-004 | Team Workshop – Product Roadmap Alignment | All Team Members | Medium | 2023-09-15 | Completed | 100% | Meeting notes and action items documented in shared drive.
T-005 | Update Project Budget Forecast | James Reed | High | 2023-09-30 | In Progress | 45% | Review cost estimates from third-party vendors.