## Worksheet
Task ID | Task Name | Assignee | Due Date | Priority | Status | Start Date | Progress (%) | Comments
T-001 | Finalize Project Scope Document | John Doe | 2024-04-15 | High | In Progress | 2024-03-30 | 65% | Needs alignment with legal team.
T-002 | <Design User Interface Mockups | Sarah Lee | 2024-04-25 | Medium | Not Started |  | 0% | Initial design phase pending feedback.
T-003 | Conduct Stakeholder Workshop | Michael Chen | 2024-04-18 | High | Scheduled | 2024-04-10 | 0% | Confirm attendance and agenda.
T-004 | Develop Backend API Structure | Lisa Wang | 2024-05-10 | High | In Progress | 2024-04-15 | 40% | Integration with database still pending.
T-005 | Prepare Training Materials | David Kim | 2024-05-01 | Low | Not Started |  | 0% | Outline to be reviewed by HR.