## Worksheet
Task ID | Task Title | Assigned To | Due Date | Priority | Status | Progress (%) | Team Collaboration Notes
T001 | Design Project Kickoff Meeting Agenda | Sarah Johnson | 2023-10-15 | High | In Progress | 60% | Team needs to align on goals, timelines, and deliverables. Include input from QA and UX.
T002 | Develop User Onboarding Flow | Michael Chen | 2023-11-01 | High | Not Started | 0% | Requires feedback from customer support team on common pain points.
T003 | Organize Biweekly Team Syncs | Emily Davis | Ongoing | Medium | Completed | 100% | Weekly check-ins with cross-functional leads. Documentation shared via Confluence.
T004 | Conduct Stakeholder Feedback Session | James Wilson | 2023-10-28 | High | Completed | 100% | Key insights recorded. Action items assigned to UX and Product teams.
T005 | Update Team Collaboration Guidelines | Linda Park | 2023-11-10 | Medium | In Progress | 45% | Need to gather input from all department heads. Draft under review.