## Worksheet
Date | Task Description | Team Member | Time Spent (hrs) | Status | Notes
2024-04-01 | Initial project planning meeting | Alex Johnson | 2.5 | Completed | Agreed on deliverables and timeline.
2024-04-03 | Design wireframes for user dashboard | Sara Lee | 3 | In Progress | Feedback requested from UX team.
2024-04-05 | Code development – login module | Marcus Kim | 4.5 | Completed | Passed QA testing.
2024-04-07 | Team sync call – progress review | All Team Members | 1.5 | Completed | Discussed blockers and next steps.
2024-04-10 | User testing session – early feedback | Lena Patel | 3.5 | Completed | Identified usability issues; updated design.