## Worksheet
Task ID | Task Description | Assigned To | Priorities | Status | Due Date | Completion % th>
#T001 | Conduct initial team alignment meeting | Jane Smith | High | In Progress | 2024-04-15 | 60%
#T002 | Create project roadmap documentBrian LeeHighPending2024-04-1830%
#T003 | Set up collaboration tools (Slack, Trello) | Alice Chen | Middle | Completed
#T004 | Organize weekly syncs scheduleLuis RodriguezMiddlePending | 2024-04-25 | 15%
#T005 | Review team performance metrics Q1Sophia KimHighPending2024-04-28 | 0%
#T006 | Draft team feedback survey questionsMorgan TaylorMediumIn Progress | 2024-04-2255%
#T007 | Finalize product feature list for v1.5Natalie ReedHighPending | 2024-05-0510%
#T008 | Prepare training materials for new hiresDaniel WuMiddlePending | 2024-04-3025%
#T009 | Host cross-department brainstorming sessionKara PatelHighIn Progress | 2024-05-0175%
#T010 | Conduct peer code reviews for Phase 2Raj PatelMiddlePending | 2024-05-105%
#T011 | Update team communication protocolsLisa WongHighPending | 2024-04-300%
#T012 | Distribute Q2 goals to all team membersJane SmithMiddleCompleted | 2024-04-15100%
End of Multi-Page To-Do List ¦ Export to Excel using standard table formatting