## Worksheet
Week | Team Member | Assigned Task | Estimated Hours | Budget Allocation ($) | Status | Deadline
Week 1 | Alex Morgan | Project Planning & Kickoff Meeting | 8 | $400 | On Track | 2024-04-05
Week 2 | Jordan Lee | Design Wireframes & User Flow | 10 | $500 | In Progress | 2024-04-12
Week 3 | Taylor Reed | Develop MVP Features | 14 | $700 | Planned | 2024-04-19
Week 4 | Sam Carter | User Testing & Feedback Loop | 6 | $300 | Scheduled | 2024-04-26
Week 5 | Morgan Hughes | Final Documentation & Reporting | 4 | $200 | Pending | 2024-05-03