## Worksheet
Day | Team Member | Task Objective | Assigned Time (HH:MM) | Status | Progress (%) | Notes / Action Items
Monday | Anna Lopez | Finalize project scope document | 09:00 - 10:30 | Completed | 100% | Approved by product owner. Ready for review.
Tuesday | James Kim | Conduct stakeholder workshop | 14:00 - 16:00 | In Progress | 75% | Attendee feedback collected; next steps scheduled.
Wednesday | Sarah Chen | Develop UI wireframes for login flow | 10:00 - 12:00 | Planned | 5% | Initial sketches ready; feedback due by Friday.
Thursday | Michael Reed | Coordinate QA testing plan | 09:30 - 11:00 | Completed | 100% | All test cases approved and assigned.
Friday | Lena Torres | Prepare weekly team sync presentation | 13:00 - 14:30 | Pending | 20% | Outline drafted; need input from dev leads.
Saturday | Team (All) | Collaborative brainstorming session | 10:00 - 12:00 | Not Scheduled | 0% | To be confirmed with team leads.
Sunday | Team (All) | Review week’s actions and feedback | 18:00 - 19:30 | Pending | 0% | Reflection report to be submitted next Monday.