## Worksheet
Week of | Team Objective | Key Activities | Responsible Members | Status (✅/⚠️/❌) | Next Steps
April 1 - April 7 | Align on Q2 product roadmap | Review market trends, gather feedback, finalize priorities | Marketing Lead, Product Manager | ✅ | Share finalized roadmap with stakeholders by April 5
April 8 - April 14 | Improve cross-functional communication | Host bi-weekly syncs, update shared documentation | Team Leads, Operations Manager | ⚠️ | Implement a shared digital workspace by April 10
April 15 - April 21 | Launch beta version of new feature | Set up testing environment, collect user feedback | Engineering Lead, UX Designer | ❌ | Postpone launch to April 23 due to integration issues
April 22 - April 28 | Conduct team performance review | Review KPIs, provide feedback, plan training | HR Manager, Team Leads | ✅ | Distribute individual development plans by April 26
April 29 - May 5 | Prepare for quarterly client presentation | Finalize content, rehearse delivery, collect input | Client Success Lead, Communications Team | ⚠️ | Add two more case studies to the presentation deck by May 2