## Worksheet
Week | Team Member | Objective | Tasks Assigned | Deadline | Status | Notes / Actions
Week 1 (Jan 6 - Jan 12) | John Doe | Finalize project scope document | Review stakeholder inputs, draft outline, present to team | Jan 9 | In Progress | Needs feedback from marketing lead by Jan 8.
Week 1 (Jan 6 - Jan 12) | Sarah Lee | Develop user onboarding flow | Create wireframes, conduct usability test with beta users | Jan 10 | Not Started | Waiting for design system approval.
Week 2 (Jan 13 - Jan 19) | Michael Chen | Coordinate sprint planning meeting | Set goals, assign tasks, finalize roadmap | Jan 15 | Scheduled | All team members to submit task priorities by Jan 14.
Week 2 (Jan 13 - Jan 19) | Lena Torres | Review client feedback report | Summarize key points, recommend improvements | Jan 18 | In Progress | Meeting with client scheduled for Jan 17.
Week 3 (Jan 20 - Jan 26) | David Kim | Conduct internal team sync | Share progress, address blockers, plan next week | Jan 25 | Not Started | Prep presentation deck by Jan 23.
Week 3 (Jan 20 - Jan 26) | Emily Wright | Prepare Q1 marketing calendar | Align with sales team, finalize events and campaigns | Jan 24 | Pending Approval | Submit to leadership by Jan 23 for review.