## Worksheet
Task | Estimated Time (hours) | Actual Time (hours) | Date Assigned | Due Date | Status
Project Planning Meeting | 2 | 1.5 | 2024-04-01 | 2024-04-03 | Completed
Design Draft Review | 3.5 | 4 | 2024-04-05 | 2024-04-10 | In Progress
Client Presentation | 4 | - | 2024-04-15 | 2024-04-18 | Pending
Team Follow-Up Meeting | 1 | 1.2 | 2024-04-20 | 2024-04-25 | Completed
Final Report Compilation | 5 | - | 2024-04-28 | 2024-05-03 | Not Started