## Worksheet
Task | Time Allocation (Hours) |  |  | Priority | Owner | Due Date
| Planned | Remaining | Completed
Project Kickoff Meeting | 2 | 1.5 | 0.5 | High | Team Lead | 2024-04-01
Requirements Gathering | 8 | 4 | 4 | High | Product Manager | 2024-04-15
Design Phase (Wireframes) | 6 | 3.5 | 2.5 | Medium | UI/UX Designer | 2024-04-25
Development Sprint 1 | 20 | 12 | 8 | High | Engineering Team | 2024-05-10
Testing & QA Review | 6 | 3 | 3 | Medium | QA Lead | 2024-05-20
Deployment & Handover | 4 | 2 | 2 | Low | DevOps Team | 2024-05-31
Total Hours (Planned) | 46 | 15.5 | 29 | —