## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status
Market Research Analysis | 2024-03-01 | 2024-03-15 | 15 | High | Jane Smith | In Progress
Product Development Phase | 2024-03-16 | 2024-04-30 | 45 | High | Alex Johnson | Planned
Customer Feedback Collection | 2024-05-01 | 2024-05-15 | 15 | Medium | Sarah Lee | Scheduled
Marketing Campaign Launch | 2024-06-01 | 2024-06-30 | 30 | High | Mike Davis | Not Started
Performance Review & Adjustments | 2024-07-01 | 2024-07-31 | 31 | Medium | Team Leadership | Planned