## Worksheet
Task | Priority Level | Estimated Time (mins) | Start Date | End Date | Assigned To | Status | Dependencies | Review Frequency
Market Research & Analysis | High | 120 | 2024-04-01 | 2024-04-15 | Marketing Team | In Progress | None | Weekly
Develop Quarterly Sales Targets | High | 90 | 2024-04-05 | 2024-04-10 | Sales Director | Planned | Market Research Complete | Bi-weekly
Team Meeting: Strategy Alignment | Medium | 60 | 2024-04-12 | 2024-04-12 | All Managers | Scheduled | Sales Targets Finalized | Monthly
Client Presentation Drafting | High | 180 | 2024-04-18 | 2024-05-01 | Client Success Lead | Pending | Strategy Alignment Meeting | Bi-weekly
Budget Reconciliation Review | Medium | 150 | 2024-04-25 | 2024-05-03 | Finance Manager | Planned | Sales Targets Approved | Monthly
Performance KPI Tracking Setup | Low | 45 | 2024-05-05 | 2024-05-10 | Operations Team | Scheduled | Budget Review Complete | Weekly
Total Tasks: 6 |  |  |  |  | Total Estimated Time: 745 minutes