## Worksheet
Task | Assigned To | Start Date | End Date | Duration (Hours) | Priority | Status | Dependencies
Market Research & Analysis | Marketing Team | 2024-03-01 | 2024-03-15 | 20 | High | In Progress | None
Product Roadmap Development | Product Management | 2024-03-16 | 2024-04-30 | 60 | High | Not Started | Market Research Complete
Client Onboarding Process | Operations Team | 2024-05-01 | 2024-05-31 | 40 | Medium | Planned | Product Roadmap Approved
Team Performance Review | HR & Leadership | 2024-06-05 | 2024-06-15 | 15 | Medium | Scheduled | Client Onboarding Live
Quarterly Strategic Planning Session | Executive Board | 2024-07-10 | 2024-07-15 | 5 | High | Not Started | All prior milestones complete