## Worksheet
Time Period | Task Category | Planned Duration (hrs) | Actual Duration (hrs) | Time Variance (hrs) | Priority | Status | Completion Rate (%) | Team Member | Project ID
Q1 - Jan to Mar | Project Planning | 40 | 38 | -2 | High | On Track | 95% | Sarah Chen | PM-001
Q1 - Jan to Mar | Market Research | 30 | 35 | 5 | Medium | Completed | 100% | David Kim | MR-005
Q1 - Jan to Mar | Team Training | 15 | 16 | 1 | Low | Completed | 106.7% | Lisa Patel | TR-009
Q2 - Apr to Jun | Product Development | 60 | 58 | -2 | High | On Track | 96.7% | James Wu | PD-012
Q2 - Apr to Jun | Client Review Meetings | 10 | 8 | -2 | Medium | On Track | 80% | Anna Liu | CR-004
Q2 - Apr to Jun | Financial Forecasting | 20 | 18 | -2 | High | On Track | 90% | Robert Tan | FF-008