## Worksheet
Task | Start Date | End Date | Duration (Days) | Dependencies | Progress (%) | Responsible | Priority
Project Kickoff & Planning | 2024-03-01 | 2024-03-05 | 5 | - | 100 | Project Manager | High
Market Research & Analysis | 2024-03-06 | 2024-03-15 | 10 | Kickoff | 85 | Business Analyst | High
Product Design & Wireframing | 2024-03-16 | 2024-04-05 | 21 | Research Complete | 70 | UI/UX Designer | Medium
Development Phase (Frontend) | 2024-04-06 | 2024-05-15 | 31 | Design Finalized | 45 | Lead Developer | High
Development Phase (Backend) | 2024-04-16 | 2024-06-15 | 61 | Frontend Complete | 30 | Backend Developer | High
Testing & QA Validation | 2024-06-16 | 2024-07-15 | 31 | Backend Complete | 60 | QA Lead | High
User Training & Onboarding | 2024-07-16 | 2024-07-31 | 16 | QA Complete | 90 | Training Specialist | Medium
Project Review & Closure | 2024-08-01 | 2024-08-05 | 5 | Training Complete | 100 | Project Manager | Low